## Slide 1
Objective and timeline
Key events
Activities
Deliverables
August
September
October
November
December
Refine Design
Software Development
Alpha Launch
Research Digerati's matching algorithm and determine how it can be applied to the fellow placement process
Continually refine webapp wireframe to meet VFA's needs
Decide on a development environment (Javascript, HTML5, Flash)
Create LAMP stack
Learn language that webapp will be developed in.
Identify potential technical issues in advance
Code most important functionality into a webapp:
Admin can add and introduce fellows and companies
Company Profiles
Fellow Profiles
Functional Messaging System
Code other features as necessary:
Needs Attention Section
Algorithmic matching
Continue to improve functionality as requested
Ensure basic usability for Spring 2013 recruiting season is bug free
Technical specifications of final product
Well defined profiles for fellows and companies
Development environment ready for coding
Webapp with company and fellow profiles, messaging system, and ability to make introductions
Add Needs Attention section, and begin to implement algorithmic matching
Launch alpha test with a few fellow and companies for bug checking
Design approval from Mike
Progress review with Mike
Progress review with Mike
Discuss rollout strategy
Launch alpha version of site